## Sheet1
1/Apr/2021
Mitsubishi Heavy Industries India
The problem list of Greenwave
In the MSIL AWC project, Greenwave has the following problems in its operations.
It is the responsibility of the main contractor to ensure that Comfort engineer (CE)
makes the necessary improvements as soon as possible.
We also request a site visit by the CE manager.
Problem list
1. Failure to meet deadlines for submission of design documents.
・Improvement plan
As indicated to us this is not a present problem but a problem that has occurred over a period of time. We are also dependant on our Vendors/manufacturers for providing the documents on time and during the Lockdown last year this follow up became quite difficult. However we do agree there were lapses when it comes to certain documents specially Panasonic. We will be more careful to make sure submissions happen on time in the future. Although we would like to point out that there has also been inordinate delay from MHI/MSIL to provide CE with details required for design and approvals of documents already submitted(For ex. Chemical dosing system, CCTV, Mizuta doors & windows not approved yet). Many times designs have been changed after complete designing has been done (For ex. Wind tunnel guide vanes, support structure etc)
2. Failure to meet deadlines for submission of monthly construction schedule.
・Improvement plan
We will get our HO involved in the submission of monthly schedules by 25th-28th of a month for the upcoming month, thereby making sure it is received by MHI on time. Last two months it was mostly site controlled.
3. Failure to meet deadlines for submission of each activity construction procedure.
・Improvement plan
We have been submitting the activity construction procedure at site but as pointed out to us that certain more details were requested from MHI which CE didnt provide. To counter this we will make a work method statement and submit along with monthly schedule with activities pertaining to that month so that any changes required can be made much in advance. At the same time we had requested MHI to share installation procedures for all MHI supplied equipment (Now provided, CE is going through it) to us in advance so that a detail can be made using that, we couldnt make any such documents for discharge nozzle as we didnt have the details until a couple of days before installation had to begin.
4. Lack of ability to planning their own schedules and procedures.
・Improvement plan
We agree many times we have faultered on our own schedules. We have faced many troubles at site with respect to availability of space and sometimes installation procedures have not gone our way and we have had to redo work. But along with that there have also been constraints from the client end such as changing of Puff panel structure due to emergency door fouling, presence of civil scaffolding and at all times we have also supported and tried to figure other ways of doing things. Having said the above we are going to depute one more engineer at site to assist Suresh Singh so that work at all ends can be monitored and will help us achieve our schedules.
5.Lack of control over the construction schedule.
・Improvement plan
We (CE) plan to keep a closer watch on weekly/monthly schedules to make sure dates are being met. A more detailed execution plan will be made from our end with deputation of one more SV and one QC.
6.No control and inspection of construction quality.
・Improvement plan
To counter this problem we suggest that we depute a Quality Supervisor at site once every 7-10 days who will make a quality report and submit it to CE for corrective action & to MHI for review.
7.Many incompleteness in the preparation of construction application documents .
(gate pass, work permit documents etc)
・Improvement plan
To counter this problem we haave hired an additional person at site reporting to our safety officer Rajesh Das. He will help MHI further in all documentation and making of permits etc.
8.Possible breach of our confidentiality agreement. (Sloppy management of data provided by us)
・Improvement plan
There has been no breach in confidentiality agreement as the data provided by MHI has not been shared with any 3rd party except Greenwave. However the other concern was that sometimes some details are asked for twice. To counter this problem we advise all documents are shared to Vikram Mehra and will be controlled and distributed within our organisations by him. Also we request MHI to keep providing us drawings & revisions of drawings & details as and when it is done as sometimes it is noticed we have been working on some old drawing.